## Plan Progress
Phase | Task | Responsible | Start | End | Days | time axis 2015-09-03 to 2016-05-08
 | time axis 2015-09-03 to 2016-05-08
1 | Confirm status of school and post 16 funding from other boroughs with ‘Re-designation’ Report and submission where appropriate
1 | Plan and create project timeline and identify relevant staff to lead and support planning process – does there need to be a recruitment process for change of role, or additional member of SLT? |  |  |  |  | #REF!
1 | Locate and quality assure relevant post 16 partners for shared and commissioned part of pathway
1 | Establish pathway support partners such as EBPs, other third sector providers, social enterprises and other employers and relevant charities. |  |  |  |  | #REF!
1 | Identify students, review data and discuss possible pathways |  |  |  |  | #REF!
1 | Identify funding streams additional to student entitlement to support programme and other pilot functions |  |  |  |  | #REF!
1 | Share and discuss plans and outcomes with stakeholders and wider school community |  |  |  |  | #REF!
1 | Appoint a Year 12 Co-ordinator to oversee preparation for students with travel training, taster days, further meetings with parents etc to work in partnership with Deputy Head for Progression (project lead) |  |  |  |  | #REF!
2 | Interview students working with Connexions and other CEIAG nominees and establish approximate numbers planning to engage with Year 12 offer |  |  |  |  | #REF!
2 | Confirm funding for Year 12 students and agree costs for commissioned part time college/provider based courses
2 | Create relevant and potential pathways and develop and organise in-house curriculum offer with focus on core timetable of English and maths |  |  |  |  | #REF!
2 | Identify/audit in-house staffing capacity and allocate to proposed timetable structure where surplus allows. |  |  |  |  | #REF!
2 | Make provisions for recruitment of additional staffing if shortfall identified or where new courses require additional expertise. |  |  |  |  | #REF!
2 | Organise college-based meetings, interviews and taster day schedule to fit in with Year 11 WRL/CEIAG timetable |  |  |  |  | #REF!
2 | Develop employer / provider links to create work experience programmes with support and mentoring where appropriate. Use links and input to create Employability course. |  |  |  |  | #REF!
2 | Develop support structure and mentoring programme via outside agencies / providers to cover transition with overlap into Year 13 |  |  |  |  | #REF!
2 | Schedule communication with students and relevant staff on progress with Year 12 planning |  |  |  |  | #REF!
2 | Hold further interviews and options process once all course availability is confirmed from ALL partners. |  |  |  |  | #REF!
2 | Ensure all Transition Planning and relevant SEN paperwork in place prior to start of Year 12
2 | Establish contracts and SLAs / Funding agreements for all partners including learning contracts for new Year 12 students
3 | Confirm delivery model and planning for in-house enrichment/ PSHCE and CEIAG
3 | Organise Enterprise/ Employability course and create network of contacts. Source accreditation where relevant
3 | Agree delivery of programmes of work-place visits via EBP / LAs and other relevant agencies to prepare learners for WRL curriculum and experiences in year 12 - this can support accredited emplyability course.
3 | Work in partnership with agencies as above to develop appropriate extended work-experience placements and potential progression support for Supported Internships
3 | Develop Course and Student Handbooks prior to end of Year 11 to support communication of relevant information
3 | Deliver an Induction Programme at end of Summer Term to prepare students for Year 12 model and 16-19 Study Programme
3 | Create a meetings and reporting schedule for pastoral and curriculum matter and to measure progress. Ensure evaluation opportunities factored in throughout academic year with reference to initial goals and utilising staff and student feedback to support process
3 | Develop regular CEIAG-focussed surveys and questionnaires to ensure learners are informed and on the correct pathways
3 | Ensure close links with partners in order to agree and plan CEIAG and plan for Year 13 progression.
| Today's Date |  | 500%
Start Date
Projected End Date
Total Man Days
Activity Planner

## Sheet2
Nonworking Date | Reason
2012-05-21 | MetLife Holiday
2012-05-22 | MetLife Holiday
2012-05-23 | MetLife Holiday
2012-05-24 | MetLife Holiday
2012-05-25 | MetLife Holiday
2012-05-28 | Memorial Day

## Sheet3
Legend
| Active Tasks | Tasks Overdue Start
| Completed Tasks (100%) | Tasks Running Late
| Non-Working Day | Non-Working Day
| Current Day | Current Day
Beyond Projected Last Day